## CR Logs
| CRs | Estimated Hours | Feedback on hours (Hussain) | Resolved Hours (Yousif) | CR Received | CR delivered | Approval Status |  | Status | Channel | SD |  |  | Comments & Feedback | Usecases
| Swap colors in the delete account popup. | 0.5 | Bug | 0 | 2023-12-15 | 2024-12-19 | Approved |  | Completed | Mobile | Shared |  |  |  | When user delets account he will be shown this
| Home |  |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Dynamic sliders Satisfaction Points | 6 | Bug | 0 | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Home - manage activities changes - | 8 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Add activity flow | 24 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| View activity | 12 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Edit activity | 10 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Delete activity | 3 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Tracker |  |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Track new flow | 24 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guide |  |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guide Main Screen - Categories | 5 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guid - Sub cateogies | 10 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guides Content -1 | 3 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guides Content -2 | 3 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guides Content -3 | 5 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Guides Content -3 | 3 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Settings |  |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Change Interests | 8 |  |  | 2023-12-01 | 2023-12-15 | Approved |  | Completed | Mobile
| Dua Section (Multiple Dua's) | 2 |  |  | 2023-12-06 | 2023-12-15 | Approved |  | Completed | Mobile
| Fiqh selection | 2 |  |  | 2024-01-08 | 2023-12-15 | Approved |  | Completed | Mobile
| Prayers Convention Selection | 4 |  |  | 2024-01-08 | 2023-12-15 | Approved |  | Completed | Mobile
| Qadrants ma color change ho ga based on the qadrant in which we are. | 2 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Activity sa kitna pahla show ho ga notification uss ke option dikhanni ha. | 2 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Remaining time in hours if it is hour/s remaining in prayers. | 1 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Loader ke tarha ak top par bar a saktee ha in the guide section. | 3 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Notification voice for Namaz will be different and for custom activities will be different. | 1 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Updating icons in activities section. | 4 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Increasing image sizes in the guide section. | 1 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| On boarding screen order needs to be changed. | 6 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Timer for delete account. |  |  |  | 2024-01-15 | 2024-01-22 | Approved |  | To Do | Mobile
| Home guide section conversion into list. | 4 |  |  | 2024-01-15 | 2024-01-22 | Approved |  | Completed | Mobile
| Edit series and edit occurrence cases for custom activity. | 16 |  |  | 2024-01-15 | 2024-01-25 | Approved |  | Completed | Mobile + BE
| Total Hours (for tasks highlighted in yellow) | 81
# | Screen | Estimated Hours |  |  | Changes | Type | Timeline | QA Comments | CR Received | CR delivered | Approval Status | Dev Status | Priority | Comments & Feedback | Channel
1 | General |  | 0 | 0 | Fonts / size need to be updated througout the app based on user feedback - Need Design Discussion with Hussain | Minor Enhancement | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
2 | General | 6 | 6 | 6 | Make App background white instead of grey - Need Design Discussion with Hussain | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
3 | General | 1 | 1 | 1 | Refine langauge on titles - Hussain to through updated figma | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
4 | General | 0.2 | 0.2 | 0.2 | Hussain to provide images for the welcome screens. | Minor enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
5 | General | 1 | 1 | 1 | Incorporate a feature to share the app at the bottom of the home page (see muslim pro as an example) | Previous request | Immediate |  |  |  | Approved | Completed |  | Completed
7 | General | 4 |  |  | Replace icons and update style on the navigation bar (e.g, use airbnb as an example) | Minor enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
8 | Home - Header | 0.1 | 0.1 | 0.1 | Display both Islamic and English dates at the top of the home page | Minor Enhancement | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
9 | Home - Header | 0.1 | 0.1 | 0.1 | Salam, [First Name only]; increase font size | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
10 | Home - Satisfation | 0.3 | 0 | 0 | Change color gradient from (Hex code: #64B9AA) to (Hex Code: #8CC8C3) to (Hex Code: #FCE697) to (Hex Code #FFD966) | Bug | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
11 | Home - Satisfation | 0.1 | 0.1 | 0.1 | Change 'how are you feeling?' to 'Daily check-in' | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
12 | Home - Satisfation | 0.1 | 0 | 0 | Remove loading icon when values are updated | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
13 | Home - Satisfation | 1 | 1 | 1 | Add an information icon next to 'How are you feeling' - Ask Hussain for content | Previous request | Immediate | Design Request as well |  |  | Approved | Completed |  | Completed
14 | Home - Satisfation | 24 | 0 | 0 | Set the default dropdown state to 'closed' to hide content initially. | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
15 | Home - Satisfation |  | 0 | 0 | Decrease the increment value for the satisfaction sliders to 2 at a time. | Previous request | Immediate |  |  |  | Approved | Completed |  | Completed
16 | Home - Satisfation |  | 20 | 20 | Replace the arrow with a pull-down bar for selection. | Design | Before Launch | Design Request as well |  |  | Approved | Completed |  | Completed
17 | Home - Satisfation |  |  |  | Implement transparency and blur effects when the dropdown is pulled down. | Design | Before Launch |  |  |  | Approved | Completed |  | Completed
18 | Home - Satisfation |  |  |  | Remove view last day / next day boxes. Add link to tracker | Design | Immediate |  |  |  | Approved | Completed |  | Completed
19 | Home - Satisfation |  |  |  | Rename the 'View last day' buttons and ' to 'today', 'yesterday', or the specific date. | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
20 | Home - Satisfation |  |  |  | Redesign the dropdown menu from vertical to horizontal orientation. | Major Enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
21 | Home - Prayer Time | 3 | 0 | 0 | Increase the text size and adjust the prayer time box accordingly. | Minor Enhancement | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
22 | Home - Prayer Time | 6 | 0 | 0 | Time left feature has too bany bugs - need to replace with standard clock counting down to next prayer (for fajr, countdown to sunrise) - Time Left should be as per Muslim Pro app - By Default - hanfi value will be selected in | Minor Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
23 | Home - Prayer Time |  | 0 | 0 | Update the time bar calculation to address the current error. | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
24 | Home - Prayer Time | 0.5 | 0.5 | 0.5 | Improve image quality for the prayer time section. | Minor enhancement | Immediate | Need Design from Client |  |  | Approved | Completed |  | Completed
27 | Schedule Today | 4 | 4 | 4 | Redesign size and content of activities shown on main schedule section - Need design discussion | Design | Before Launch |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
28 | Schedule Today | 5 | 5 | 5 | Add ability to check-off what activity has been completed (including prayers) - remove ability to track from elsewhere on home screen | Major Enhancement | Before Launch | Need Design from Designer |  |  | Approved | Completed |  | Completed
30 | Schedule Today | 48 | 0 | 0 | Ability to add custom activity on Schedule (without going through full flow of selecting domain, goal, activity) | Major Enhancement | Before Launch | Need Design from Designer |  |  | Approved | Completed |  | Completed
31 | Schedule Today |  | 0 | 0 | Replace icons of each category in the first screen with images from the guide screen (remove mobile screen from background) | Design | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
32 | Schedule Today | 2.5 | 0 | 0 | Redesign activity seclection pages ensuring cleand design, no missing words, and consistent spacing. | Design | Immediate |  |  |  | Approved | Completed |  | Completed
33 | Schedule Today | 1 | 1 | 1 | For final activity screen, redesign should include minimal text summary (to be provided by Hussain), and option to expand more if user desires | Design | Before Launch | Need Design from Designer/Client |  |  | Approved | Completed |  | Completed
34 | Schedule Today | 2 | 0 | 0 | Color of screen is not white when the text pops up. Text has to be formatted properly in terms of spacing and where the bullet points are included | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
36 | Schedule Today |  | 0 | 0 | Duration and Reminder Options not consistent with input shared previously | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
37 | Schedule Today | 1 | 0 | 0 | Format of dropdown not consistent with remaining page | Bug | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
38 | Schedule Today | 8 | 0 | 0 | For Monthly reccuring pattern, top of dates should include a letter for the day, like typical calendars | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
39 | Schedule Today | 1 | 1 | 1 | Option to view date in both islamic and english calendar | Minor enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
40 | Schedule Today |  | 0 | 0 | Option for user to rename reminder to a custom text | Minor enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
41 | Schedule Today | 1 | 1 | 1 | On the yearly recurrence pattern both islamic and other calendar option should appear | Minor enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
43 | Home - Fasting Tracker | 4 | 0 | 0 | Include an 'undo' option for the fasting time tracker to correct accidental taps or fasts. | Minor Enhancement | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
44 | Home - Quran Tracker | 8 | 0 | 0 | Remove as a separate tracker - to be included as activity if the user adds it to their schedule. User can track if they've read it from there | Major Enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
45 | Home - Quran Tracker | 4 | 0 | 0 | Remove as a separate tracker - to be included as activity if the user adds it to their schedule. User can track if they've prayed from there | Major Enhancement | Before Launch |  |  |  | Approved | Completed |  | Completed
46 | Home - Articles | 2 | 0 | 0 | Remove the image and text from the carousel design in the articles section to decide on layout. | Previous request | Immediate | Need more details from design side | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
47 | Home - Articles | 0.5 | 0 | 0 | Article titles should only reflect only the title, not the category. | Minor Enhancement | Immediate | Need more details from design side |  |  | Approved | Completed |  | Completed
48 | Home - Articles | 1 | 1 | 1 | Add tags for category an article below the title | Minor Enhancement | Immediate | Need more details from design side |  |  | Approved | Completed |  | Completed
50 | Home - Articles | 1 | 0 | 0 | On the carosel, when you click "read more" it should navigate to article not the guide section | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
51 | Daily Hadith | 6.2 | 0 | 0 | (Previously Daily dua) Update the 'Daily Dua' section to reference Hadith appropriately. Add Title | Minor Enhancement | Immediate | Update text as per my understanding | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
55 | Home - Hajj | 0.2 | 0 | 0 | Should be clickable and Naviagte to settings for Hajj Goal | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
56 | Qibla Finder | 0.2 | 0.2 | 0.2 | Update Image on Qibla Finder - Hussain to provide | Design | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
57 | Qibla Finder | 0.1 | 0.1 | 0.1 | Hussain to provide updated text for yellow text box | Design | Immediate |  |  |  | Approved | Completed |  | Completed
58 | Qibla Finder | 0.2 | 0.2 | 0.2 | Update color of yellow box to green (#64B9AA) when facing the Qibla | Major Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
59 | Qibla Finder | 1 | 0 | 0 | Calibartion of direction ? "Qibla is at 54.35" Between 50 and 59 its giving all Makkah. Can this be made more sensitive? | Major Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
60 | Tracker | 16 | 0 | 0 | Enable user to input all fields on the tacker screen | Minor Enhancement | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
61 | Tracker | 8 | 0 | 0 | Make satisfaction theme consistent with other charts, and home page | Design | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
62 | Tracker | 2 | 2 | 2 | Add information icons throughout to clarify the meaning of each field | Previous request | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
63 | Fasting | 8 | 0 | 0 | Enable updates to the fasting tracker directly from the fasting page. | Previous request | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
64 | Prayer |  | 0 | 0 | Update Images for Prayer - Hussain to see if higher resolution images are available | Design | Immediate |  |  |  | Approved | Completed |  | Completed
65 | Prayer | 2 | 2 | 2 | Add image for sunrise - Hussain to provide | Design | Immediate |  |  |  | Approved | Completed |  | Completed
66 | Prayer | 1 | 1 | 1 | Show timing of sunrise after Fajr | Minor enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
67 | Prayer | 1 | 0 | 0 | Show date consistently throughout the app | Design | Immediate |  |  |  | Approved | Completed |  | Completed
68 | Quran | 0 | 0 | 0 | On Quran home screen, text of Surahs needs to be changed - example is Quran.com | Design | Immediate | Need Design from Designer | 2024-02-05 | 2024-03-01 | Pending | To Do |  | Completed
69 | Quran | 0.2 | 0 | 0 | On Quran home screen, shift the stars and surahs to the left. | Design | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
72 | Quran | 1 | 1 | 1 | Increase Arabic text size - see Muslim Pro as an example | Design | Immediate | Need Design from Designer |  |  | Approved | Completed |  | Completed
73 | Quran | 16 | 0 | 0 | Update the ability to continue playing even when the phone screen goes off | Major Enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
74 | Quran | 1 | 1 | 1 | Add information icon indicating the translator for the translation of the Quran | Design | Immediate |  |  |  | Approved | Completed |  | Completed
77 | Guide |  |  |  | Size of images is too small - Hussain to provide actuals | Immediate | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
78 | Guide | 2 | 2 | 2 | Move to a tile structure with bigger images and text on it - Ask Hussain for sample | Design | Immediate |  |  |  | Approved | Completed |  | Completed
79 | Guide | 1 | 0 | 0 | Image size on the carousel needs to be bigger (fit 2 on the same page) | Design | Immediate |  |  |  | Approved | Completed |  | Completed
80 | Guide |  | 0 | 0 | Complete High Quality Images for the App - Hussain to provide | Image Generation | By 20th of Feb |  |  |  | Approved | Completed |  | Completed
81 | Guide | 3 | 0 | 0 | Text formatting for articles need to be checked. | Complete Article Drafts | By 28th of Feb |  |  |  | Approved | Completed |  | Completed
82 | Guide |  |  |  | Title should go under the image, sections need to be created. | Design | Immediate |  |  |  | Approved | Completed |  | Completed
83 | Guide | 1 | 1 | 1 | Have a green line on top to show the progess for each article as you read i | Minor enhancement | Immediate |  |  |  | Approved | Completed |  | Completed
85 | Zakat Calculator | 4 | 0 | 0 | Add information for each category in the calculator explaining what it is and how it is calculated - Align with Hussain | Previous request | Immediate |  | 2024-02-05 | 2024-03-01 | Approved | Completed |  | Completed
86 | Zakat Calculator | 1 | 0 | 0 | Automatically remove 0 wheen clicking on any field in the Zakat Calculator | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
87 | Zakat Calculator | 1 | 0 | 0 | Add comas on the Zakat field | Bug | Immediate |  |  |  | Approved | Completed |  | Completed
88 | Welcome Screens | 1 | 1 | 1 | text and images are changed on all onboarding screens + Splash screen | Change | Immediate |  | 2024-02-26 | 2024-03-01 | Approved | Completed |  | Completed
89 |  | 3 | 3 | 3 | Logo changed thorughout the app. and in place holders as well | Change |  |  |  |  | Approved | Completed |  | Completed
90 |  | 1.5 | 1.5 | 1.5 | Satisfaction points info icons data along with all the other data that was pending from the client's side is all provided. | Change |  |  |  |  | Approved | Completed |  | Completed
92 |  | 2 | 0 | 0 | Activity should be open by default in the schedule screen. Also after creating an activity, it should be open. | Minor Enhancement |  |  | 2024-03-04 |  | Approved | Completed
93 |  | 0.3 | 0.3 | 0.3 | Add location on the Home screen as per change in Figma design | Minor Enhancement |  |  |  |  | Approved | Completed
94 |  | 0.5 | 0 | 0 | The notification reminder of Namaz should be changed. As per the client, it should be reminded at the time of namaz as of now. | Minor Enhancement |  |  |  |  | Approved | Completed
95 |  | 1 | 0 | 0 | Images of the app scheme should change for namaz on both the Home and prayer screens. | Minor Enhancement |  |  |  |  | Approved | Completed
96 |  | 3 | 3 | 3 | The upcoming Namaz feature needs to be updated as per the client. | Minor Enhancement |  |  |  |  | Approved | Completed
97 |  | 0.2 | 0.2 | 0.2 | Change the color of the sunrise on the prayer screen to yellow but placement will remain the same after fajar. | Minor Enhancement |  |  |  |  | Approved | Completed
98 |  | 0.4 | 0.4 | 0.4 | Replace the icons with the corrected ones now. | Minor Enhancement |  |  |  |  | Approved | Completed
99 |  | 0.4 | 0 | 0 | Reverse the white space in the satisfaction scroll. | Minor Enhancement |  |  |  |  | Approved | Completed
101 |  | 0.4 | 0 | 0 | Font size needs to be increased more. | Bug |  |  |  |  | Approved | Completed
| General | 0 | 0 | 0 | the whole of the app will have urbanist font | Major Enhancement |  |  | 2024-03-04 |  | Approved | Completed
| Guide Screen | 0.5 | 0 | 0 | Headings in the guide section should be bold as in the data provided. | Minor Enhancement |  |  |  |  | Approved | Completed
| Backend |  |  |  | are there any other options and are they stable for namaz timings | [5 empty] | Approved | Completed
| Home |  |  |  | Dropdown UX not consistent of satisfaction | Bug |  |  | 2024-03-11 |  | Approved | Completed
| General |  |  |  | Loaders should be removed completely | Major Enhancement |  |  |  |  | Approved | Completed
| General | 0.5 | 0 | 0 | tap needed again and again to open the info icon | Bug |  |  |  |  | Approved | Completed
| General |  |  |  | font size par ak session chahiya, including all stake holders | [5 empty] | Approved | Completed
| Home | 1 | 0 | 0 | surface area for tapping should be increased for the dropdown bar of satisfaction points on home screen | [5 empty] | Approved | Completed
| Home & Tracker | 2 | 2 | 2 | colors of the satisfaction points on home screen should be according to the quadrant (Added in figma 3.0) | Minor Enhancement |  |  |  |  | Approved | Completed
| Tracker | 1 | 0 | 0 | date on the calendar should be tapable (Tracker Screen On top Calendar) | [5 empty] | Approved | Completed
| Tracker | 0.5 | 0.5 | 0.5 | Need to display prayer dot in tracker screen current date (currently it hides under the star) | Minor Enhancement |  | same as task in row 160 |  |  | Approved | Completed
[5 empty] | need to discuss our approach on what will happen when all 5 prayers are prayed in the tracker section on the calendar | Major Enhancement |  |  |  |  | Pending | To Do | Don't action - to be discussed later
|  | 0.1 | 0.1 | 0.1 | Update image for sunrise - Hussain to provide | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.5 | 0.5 | 0.5 | there should be a tag under the articles on the home screen as well. Image sent in whatsapp of halo app. |  |  | Same as task in row 165 |  |  | Approved | Completed
|  | 0.2 | 0 | 0 | 'A' should be capital in splash screen. | Bug |  |  | 2024-03-09 |  | Approved | Completed
|  | 5 | 0 | 0 | Prayers timings needs to be same as explained in the recording. | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.5 | 0 | 0 | Location label on the home screen should redirect to the location | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.5 | 0.5 | 0.5 | Update check icon to radio buttons in prayers section | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 1 | 0 | 0 | Hadith popup screen should have same size and font as we tap on any namaz on the home screen | Bug |  |  |  |  | Approved | Completed
|  | 2 | 0 | 0 | Tapping on home screen namaz should navigate the user to the detail screen similar to that in Activity | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | "if" missing in the main Hadith on the home screen | Bug |  |  |  |  | Approved | Completed
[5 empty] | Qibla screen par spelling of 'Makkah' hoona chahiya, as in figma. | Bug |  |  |  |  | Approved | Completed
[5 empty] | Home Screen Tracker should retain the same value as previously entered. | Bug |  |  |  |  | Approved | Completed
[5 empty] | Custom activity par bhee dropdown values updated honi chahiyaan. | [5 empty] | Approved | Completed
|  | 0.5 | 0.5 | 0.5 | Hide labels of days in recurring, monthly. (custom,and selection from list) | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 3 | 3 | 3 | Prayers and Quran should be accessable in guest mode as well | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.1 | 0.1 | 0.1 | Update Quran notification | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.1 | 0.1 | 0.1 | Quran Settings screen ma notification ka label change karna ha. | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Alignment of the speaker icons needs to be fixed | Bug |  |  |  |  | Approved | Completed
[5 empty] | Update names of surah font to same as in quran.com | Minor Enhancement |  |  |  |  | Pending | To Do | Low
[5 empty] | Goals mapping is in the activities doc. Need to add that in the articles section | Data Input |  |  |  |  | Completed | Completed |  | This is meant to be category mapping, not goal mapping
|  | 2 | 2 | 2 | Prayers section ma date wise back and forth ho sakta ha. | Minor Enhancement |  | same as task in row 167 |  |  | Completed | Completed |  | Need the 30 days, not just 1 day. My comment was that it's ok to not go beyond 30 days.
[5 empty] | Need to forward the data in the app to the next day on the satisfaction points. | Bug |  |  | 2024-03-12 |  | Approved | Completed |  | Problem: If I go to the tracker without pulling down the the daily check-in pull-down, tracker shows all values as zero.
|  | 0.1 | 0.1 | 0.1 | Grey color in the tracker section should be replaced with green of the activities section on the home screen. | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.5 | 0.5 | 0.5 | Remove the star. | Minor Enhancement |  |  |  |  | Approved | Completed |  | Approved, but the font for the other dates selected are mismatched (ends up being larger than the current date, and dot moves down)
|  | 1 | 0 | 0 | Tag on top for guides on the home screen. | Minor Enhancement |  |  |  |  | Approved | Completed |  | Tags are incorrect - these are supposed to be the 12 categories
|  | 0.1 | 0.1 | 0.1 | Increase the size of the editor in Hadith section editor. | Minor Enhancement |  |  |  |  | Approved | Completed |  | ??
|  |  | 0 | 0 | The styling should look exactly the same as it does on the mobile app. | Bug |  |  |  |  | Approved | Completed |  | What happended to the font size????
|  |  | 0 | 0 | Ordering of the articles should be same as in the guides file. | Bug |  |  |  |  | Approved | Completed
[5 empty] | Need to increase size of the text box in admin portal for content management & add bullet points to it | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Update colors of satisfaction graph | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | In the prayers section, we need to have arrows to navigate to next or previous date | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 0.5 | 0.5 | 0.5 | Need to update maghrib text from "End the day with Maghrib reflection" to "Begin your evening with Maghrib" | Minor Enhancement |  |  |  |  | Approved | Completed
Bill calculated uptil this point
[5 empty] | In the tracker screen, if I scroll the bar to maximum i.e.100 the third digit does not display instead it appears as "10" instead of "100" | Bug |  |  |  |  | Approved | Completed
[5 empty] | Fix font size of the article section | Bug |  |  |  |  | Approved | Completed
[5 empty] | Upon opening the app and navigating directly to the tracker screen, doesnot display the tracker section. When you open the app and go straight to tracker, can’t scroll to satisfactiom bars, or sometimes you can scroll, but they are zero. Then you go to the home screen and pull down on daily check in, the values are all there. After that, you go back and it starts to appear again. | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | In case if the app is left in the background for sometime and reopened again the prayer times donot update (there should be an update procedure in place once the appcomes from background to foreground) | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | In the tracker screen -> Quran tracker, there is a typo "Have you read the the Quran?" | Bug |  |  |  |  | Approved | Completed
[5 empty] | On the tracker screen -> Calendar, the selected date needs to be made un-bold in order to keep the number in one line | Minor Enhancement |  | yousif to confirm this; fixed |  |  | Approved | Completed
[5 empty] | On the prayer screen, the radio buttons should be a larger circle with green outline instead of grey, and the inside circle can be the same | Minor Enhancement |  |  |  |  | Pending | To Do | Low
[5 empty] | If the user taps on "I am fasting" the sehar and iftar times tag should automatically appears on respective prayers | Minor Enhancement |  |  |  |  | Pending | To Do | High | we have some edge cases that we need to discuss
[5 empty] | If Imsak is clicked, the tag should say Imsak: and the time for sehar and iftar | Minor Enhancement |  |  |  |  | Pending | To Do | High | need elaboration
[5 empty] | Fix satisfaction bar chart, and anchor it with date | Major Enhancement |  |  |  |  | Pending | To Do | TBD
[5 empty] | Update logos in email | Minor Enhancement |  |  |  |  | Approved | Completed |  | QA will validate
[5 empty] | "For Duration: 15 mins, 30 mins, 1 hour, and 3 hours For Reminders: 15 mins, 30 mins, 1 hour, 24 hours" | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | Change images for the pre-defined activities https://www.figma.com/file/Tc2nWYZS91n5oUZMSygZg5/Ruhiy-3.0?type=design&node-id=0-1&mode=design&t=qvcw5nj2hrJHlCfn-0 | Minor Enhancement |  |  | 2024-03-15 |  | Approved | Completed | High
[5 empty] | Adding any activity changes the time of the read quran activity to current time. E.g., I added an activity to add Personal care time, and it updated the read quran tag to the current local time (2:11am). Also, the tag says “Manual Activity”, when it should say “Faith”. Ordering of activity has been changed; they appear at the end | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | Option to update activity content on the admin portal | Major Enhancement |  |  |  |  | Pending | To Do | Medium
[5 empty] | Add tag/toggle on each article for the admin portal to allow the admin to select which article to display for the satisfaction points; | Major Enhancement |  |  |  |  | Pending | To Do | Medium
|  | 19 |  |  | Featured Articles on home screen (similar to news or blog); keep title dynamic and toggle on admin portal to be able to disable later on | Major Enhancement |  |  |  |  | Pending | In Progress | Medium | Yousif to get timeline on this
|  | 5 |  |  | Update prayers schedule section & activity on home screen to carousel view (hassan design) and fasting button | Major Enhancement |  |  |  |  | Approved | In Progress | High | Yousif to get timeline on this
|  | 8 |  |  | Update planner/calendar screen design to: https://www.figma.com/file/52IMZkiYyKbDBpb9IfUMHi/%E2%9C%B3%EF%B8%8F-Ruhiy-4.0-(Internal)?type=design&node-id=2180-7&mode=design&t=E1ucGVStAvx4NY2K-0 | Minor Enhancement |  |  |  |  | Pending | In Progress
Add calendar page to the home screen
[5 empty] | Update hex code of quadrant on satisfaction tracker (yellow colour) | Minor Enhancement |  |  |  |  | Approved | Completed | High
[5 empty] | New activities are added at the end of the day, and not sequenced properly | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | Tracking values of prayers not unchecking for the next day. | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | Satisfaction screen in tracker (with white background); make the the scroll white with green outline instead of full green | Minor Enhancement |  |  |  |  | Approved | Completed | High
[5 empty] | Prayers screen; the date arrows should allow 30+- days | Minor Enhancement |  |  |  |  | Pending | To Do | Medium
[5 empty] | Ramadan date says 8th Ramadan for Islamabad. (muslim pro says 7th), need to verify the data | Bug |  |  |  |  | Approved | Completed | High
[5 empty] | Once, the iftar counter goes to "0"; ideally it should disappear (get an idea on this from the designer) | Minor Enhancement |  |  |  |  | Pending | To Do | Low
[5 empty] | Add Force update in the app (configurable on the admin portal) | Major Enhancement |  |  |  |  | Approved | Completed | Critical
[5 empty] | Fasting page revamp | Major Enhancement |  |  |  |  | Pending | To Do |  | need to discuss with hussain
[5 empty] | Hanafi & Shafi times not updating in the app (prayer convention of shi'a not updating) | Bug |  |  |  |  | Approved | Completed | Critical
[5 empty] | Users keep getting the enable notification pop up even if the user taps "Do not notify me" | Bug |  |  |  |  | Pending | To Do | High
[5 empty] | Prayer convention needs to be added in the signup screen as well | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Link the backstack of the pages especially in the guide section of the admin portal | Bug |  |  |  |  | Pending | To Do | High
[5 empty] | Deactivate guide, click the collapse. The guide activates automatically (admin portal) | Bug |  |  |  |  | Pending | To Do | High
[5 empty] | Basic user journey mapping/data points/heat map | Major Enhancement |  |  |  |  | Pending | To Do
[5 empty] | "Register here" need to be made bold on the signup screen (see the font figma) | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Values of the satisfaction points get's reset at new login of the same account | Bug |  |  |  |  | Pending | To Do
[5 empty] | Change the label 'Fiqh' to 'Asr Calculation' in prayer settings screen bring "Prayer convention" above "Select Fiqh" in the prayer settings screen | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | The styling/spacing needs to improve in the OTP email, so that the OTP code does not goes to the next line | Bug |  |  |  |  | Pending | To Do
[5 empty] | Need to add the convention option for the prayers on the onbording screens as well | Minor Enhancement |  |  |  |  | Approved | Completed
|  | 8 |  |  | if the user is not updating the satisfaction levels; next day the same scores remain and the articles & hadith stay the same. In such a case we need to show another article & hadith to the user from the same category (as per the satisfaction score calculation) | Major Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Custom notification option on the Admin portal | Major Enhancement |  |  |  |  | Pending | To Do
[5 empty] | Subtext to be added throughout the fields in the app for prayer conventions etc | [5 empty] | Pending | To Do
[5 empty] | what is the default prayer convention | [5 empty] | Pending | To Do
|  | 2 |  |  | Bottom bar updates: Add "more" icon in place of "guide", "guide" to come in place of "fasting" icon. Hide "Fasting" icon on the bottom bar. | Minor Enhancement |  |  |  |  | Approved | Completed
[5 empty] | Satisfaction drawer (Home Screen): Bring back the arrow icon on the drawer as in the (ruhiy 2.0) design | [5 empty] | Pending | To Do
|  | 16 |  |  | Search in guides, quran | Major Enhancement |  |  |  |  | Approved | Completed |  | Yousif to get timeline on this
[5 empty] | Search history | [5 empty] | Pending | To Do |  | Yousif to get timeline on this
[5 empty] | Bookmark an article/ Add to favourite | [5 empty] | Pending | To Do
[5 empty] | Articles & Hadith should update on the next date regardless of the scores | [5 empty] | Pending | To Do
[5 empty] | Signin needs to be consistent on the onboarding screens | Bug |  |  |  |  | Approved | Completed
[5 empty] | If the user travels to a different time zone, there should be a popup notifying the user about the timezone change and state the set prayer convention and ask if the user wants to keep the same settings or change | Minor Enhancement |  |  |  |  | Approved | Completed
Check Prayer time API's flexibility
Period tracker
|  | 9 |  |  | Popup to the user upon time zone change, the prayer settings should update once the user agrees to update according to the time zone | Enhancement |  |  |  |  | Approved | Completed
|  | 12 |  |  | Shimmer effect in all over the app | Enhancement |  |  |  |  | Approved | Completed
|  | FREE |  |  | Update splash screen animation | Enhancement |  |  |  |  | Approved | Completed
|  | 6 |  |  | Make the activity section auto scrollable to the current activity | Enhancement |  |  |  |  | Approved | Completed
|  | 22 |  |  | Quran player to stay fixated at the bottom, if the quran is being played and the user can navigate within the app anywhere (reference Youtube) Quran Media Player | Enhancement |  |  |  |  | Pending | To Do
[5 empty] | Activity Grouping on carousel | Enhancement |  |  |  |  | Pending | To Do
|  | 110 |  |  | Mood Check-in + Keep Satisfaction development intact and comment it out for later use | Enhancement | [7 empty] | Yousif to get timeline on this
Yousif to get timeline on this
|  |  | Disputed Hours (Resolved) |  | Enhancement Batch 1 | Enhancement Batch 2 | Quran Media Player | Mood Check-In
| Total dev hours: | 359.6 | 74 |  | 58 | 27 | 22 | 110
| QA: | 35.96 | 7.4 |  | 5.8 | 2.7 | 2.2 | 11
| PM | 107.88 | 22.2 |  | 17.4 | 8.1 | 6.6 | 33
| Total billable hours | 503.44 | 103.6 |  | 81.2 | 37.8 | 30.8 | 154
| Total Cost | 15103.2 | 3108 |  | 2436 | 1134 | 924 | 4620

## FeedbackGood to Have
Thoughts/Good to have features | Hours
- Plz make dark mode
- intuitive interface. Found all the main features really quick.
- on tracker page, clicking a prayer done causes a loading screen for a second. Doesn't happen on home screen. I like no loading screen.
- I like the (prayer) habit tracking feature. Some reason to keep streaks going like showing a full few weeks of history that you color in (see various habit tracking apps on Android) or charting / analytics may encourage more use and habit forming.
- Notifications for key days and zakat is cool. Is it team hilal or team calculation?
Should be able to see timings of the prayers for the whole month in the prayers section